## Sheet1
S.NO | Station Name | Station Code | Zone(s) | Station Id | Abs Location | EI Make | Milestone | Section | KAVACH Type | Installation Status | 200KB DATS Status | DATS Completion Date | IFAT Status | IFAT Completion Date | IFAT Report | Comments - [ iFAT ] | CFAT Status | CFAT Completion Date | CFAT Report | Comments - [ cFAT ] | EI OEM Logic Loading Status | SAT Status | SAT Completion Date | SAT Report | Comments - [ SAT ]
1 | Maripat | MIU | NCR-A | 37001 | 1422.446 |  | MILESTONE-2 | Section#1: CPYZ-Tundla | S |  | Completed | 2025-05-07 | Completed | 2025-08-12 | Yes | 160 KMPH DATS Tested and Sent to field | Completed and Signed by Rly. | 2025-11-25 |  | 160KMPH Dats Tetsing Completed. |  | Work In Progress
2 | Dadri | DER | NCR-A | 37002 | 1415.69 |  | MILESTONE-2 | Section#1: CPYZ-Tundla | S |  | Completed | 2025-09-16 | Completed | 2025-11-04 | Yes | 160 KMPH DATS Tested and Sent to field | Work In Progress |  |  | 160KMPH Testing In Progress. |  | Work In Progress
3 | LSC-5 | DER-LSC-5-AJR | NCR-A | 37003 | 1412.188 |  | MILESTONE-2 | Section#1: CPYZ-Tundla | L |  | Completed | 2025-05-27 | Completed | 2025-10-13 | Yes | 160 KMPH DATS Tested and Sent to field | Work In Progress |  |  |  |  | Pending
4 | Ajaibpur | AJR | NCR-A | 37004 | 1406.482 |  | MILESTONE-1 | Section#1: CPYZ-Tundla | S |  | Completed | 2025-05-27 | Completed | 2025-09-14 | Yes | 160 KMPH DATS Tested and Sent to field | Completed and Signed by Rly. | 13-09-2025 11-02-2026 |  | 160KMPH Dats Tetsing Completed. Tag ABS Locations Changed Dats Testing Completed |  | Completed & Signed by Raiways | 2025-02-27
5 | Dankoure | DKDE | NCR-A | 37005 | 1398.02 |  | MILESTONE-1 | Section#1: CPYZ-Tundla | S |  | Completed | 2025-05-27 | Completed | 2025-08-04 | Yes | 160 KMPH DATS Tested and Sent to field | Completed and Signed by Rly. | 2025-09-09 |  | 160KMPH Dats Tetsing Completed. |  | Completed & Signed by Raiways | 2025-08-10
6 | LSC-10 | DKDE-LSC-10-WIR | NCR-A | 37006 | 1392.383 |  | MILESTONE-1 | Section#1: CPYZ-Tundla | L |  | Completed | 2025-05-27 | Completed | 2025-07-25 | Yes | 160 KMPH DATS Tested and Sent to field | Completed and Signed by Rly. | 2025-08-20 |  | 160KMPH Dats Tetsing Completed. |  | Completed & Signed by Raiways | 2025-02-28
7 | Wair | WIR | NCR-A | 37007 | 1389.451 |  | MILESTONE-1 | Section#1: CPYZ-Tundla | S |  | Completed | 2025-05-27 | Completed | 2025-08-06 | Yes | 160 KMPH DATS Tested and Sent to field | Completed and Signed by Rly. | 2025-08-23 |  | 160KMPH Dats Tetsing Completed. |  | Completed & Signed by Raiways | 2025-08-27
8 | Chola | CHL | NCR-A | 37008 | 1384.13 |  | MILESTONE-1 | Section#1: CPYZ-Tundla | S |  | Completed | 2025-05-27 | Completed | 2025-08-09 | Yes | 160 KMPH DATS Tested and Sent to field | Completed and Signed by Rly. | 2025-08-25 |  | 160KMPH Dats Tetsing Completed. |  | Completed & Signed by Raiways | 2025-09-12
9 | LSC-13 | CHL-LSC-13-SKQ | NCR-A | 37009 | 1378.67 |  | MILESTONE-1 | Section#1: CPYZ-Tundla | L |  | Completed | 2025-05-27 | Completed | 2025-08-13 | Yes | 160 KMPH DATS Tested and Sent to field | Completed and Signed by Rly. | 2025-04-09 |  | 160KMPH Dats Tetsing Completed. |  | Completed & Signed by Raiways | 2025-02-20
10 | Sikandarpur | SKQ | NCR-A | 37010 | 1375.386 |  | MILESTONE-1 | Section#1: CPYZ-Tundla | S |  | Completed | 2025-05-27 | Completed | 2025-08-21 | Yes | 160 KMPH DATS Tested and Sent to field | Completed and Signed by Rly. | 2025-08-30 |  | 160KMPH Dats Tetsing Completed. |  | Completed & Signed by Raiways | 2025-03-04
11 | Khurja | KRJ | NCR-A | 37011 | 1369.82 |  | MILESTONE-2 | Section#1: CPYZ-Tundla | S |  | Completed | 2025-05-27 | Completed | 2025-08-20 | Yes | 160 KMPH DATS Tested and Sent to field | Completed and Signed by Rly. | 2025-09-23 |  | 160KMPH Dats Tetsing Completed. |  | Work In Progress
12 | LSC-17 | KRJ-LSC-17-DAR | NCR-A | 37012 | 1364.934 |  | MILESTONE-2 | Section#1: CPYZ-Tundla | L |  | Completed | 2025-05-27 | Completed | 2025-08-05 | Yes | 160 KMPH DATS Tested and Sent to field | Completed and Signed by Rly. | 2025-09-16 |  | 160KMPH Dats Tetsing Completed. |  | Work In Progress
13 | Danwar | DAR | NCR-A | 37013 | 1358.736 |  | MILESTONE-2 | Section#1: CPYZ-Tundla | S |  | Completed | 2025-05-27 | Completed | 2025-10-27 | Yes | 160 KMPH DATS Tested and Sent to field | Completed and Signed by Rly. | 2025-08-28 |  | 160KMPH Dats Tetsing Completed. |  | Completed & Signed by Raiways
14 | ECU-26 | DAR-ECU-26-SOM | NCR-A | 37014 | 1353.402 |  | MILESTONE-2 | Section#1: CPYZ-Tundla | L |  | Completed | 2025-05-27 | Completed | 2025-08-04 | Yes | 160 KMPH DATS Tested and Sent to field | Completed and Signed by Rly. | 2025-08-20 |  | 160KMPH Dats Tetsing Completed. |  | Completed & Signed by Raiways
15 | Somna | SOM | NCR-A | 37015 | 1348.54 |  | MILESTONE-2 | Section#1: CPYZ-Tundla | S |  | Completed | 2025-05-27 | Completed | 2025-08-21 | Yes | 160 KMPH DATS Tested and Sent to field | Completed and Signed by Rly. | 2025-08-25 |  | 160KMPH Dats Tetsing Completed. |  | Completed & Signed by Raiways
16 | LSC-22 | SOM-LSC-22-KLA | NCR-A | 37016 | 1343.768 |  | MILESTONE-2 | Section#1: CPYZ-Tundla | L |  | Completed | 2025-05-27 | Completed | 2025-08-04 | Yes | 160 KMPH DATS Tested and Sent to field | Completed and Signed by Rly. | 2025-11-07 |  |  |  | Completed & Signed by Raiways
17 | Kulwa | KLA | NCR-A | 37017 | 1338.401 |  | MILESTONE-2 | Section#1: CPYZ-Tundla | S |  | Completed | 2025-05-27 | Completed | 2025-10-29 | Yes | 160 KMPH DATS Tested and Sent to field | Completed and Signed by Rly. | 2025-08-29 |  | 160KMPH Dats Tetsing Completed. AFTC Removed Dats Testing InProgress |  | Completed & Signed by Raiways
18 | Mehrawal | MWUE | NCR-A | 37018 | 1332.737 |  | MILESTONE-2 | Section#1: CPYZ-Tundla | S |  | Completed | 2025-05-27 | Completed | 2025-10-28 | Yes | 160 KMPH DATS Tested and Sent to field | Completed and Signed by Rly. | 2025-10-06 |  | 160KMPH Dats Tetsing Completed. AFTC Removed Dats Testing In Progress |  | Completed & Signed by Raiways
19 | Aligarh | ALJN | NCR-A | 37019 | 1326.52 |  | MILESTONE-2 | Section#1: CPYZ-Tundla | S |  | Completed | 2025-05-27 | Completed | 2026-01-30 |  | 160 KMPH DATS Tested and Sent to field | Work In Progress |  |  |  |  | Work In Progress | 2026-02-17 |  | 160KMPH Testing In Progress
20 | Daudkhan | DAQ | NCR-A | 37020 | 1319.46 |  | MILESTONE-2 | Section#1: CPYZ-Tundla | S |  | Completed | 2025-05-27 | Completed | 2026-01-22 |  | 160 KMPH DATS Tested and Sent to field | Completed and Signed by Rly. | 2026-01-29 |  |  |  | Work In Progress | 2026-10-02 |  | 160KMPH Testing In Progress
21 | Mandrak | MXK | NCR-A | 37021 | 1312.57 |  | MILESTONE-2 | Section#1: CPYZ-Tundla | S |  | Completed | 2025-05-27 | Completed | 2025-07-05 | Yes | 160 KMPH DATS Tested and Sent to field | Completed and Signed By Rly. | 29-07-2025 07-01-2026 |  | 160KMPH Dats Tetsing Completed. AFTC Removed Dats Testing Completed |  | Completed & Signed by Raiways | 2025-08-05
22 | Sasni | SNS | NCR-A | 37022 | 1305.28 |  | MILESTONE-2 | Section#1: CPYZ-Tundla | S |  | Completed | 2025-05-27 | Completed | 2025-06-23 | Yes | 160 KMPH DATS Tested and Sent to field | Completed and Signed By Rly. | 2025-07-29 |  |  |  | Completed & Signed by Raiways | 2025-07-29
23 | LSC-35 | SNS-LSC-35-HRS | NCR-A | 37023 | 1302.17 |  | MILESTONE-2 | Section#1: CPYZ-Tundla | L |  | Completed | 2025-05-27 | Completed | 2025-07-08 | Yes | 160 KMPH DATS Tested and Sent to field | Completed and Signed By Rly. | 2025-07-25 |  |  |  | Completed & Signed by Raiways | 2025-08-11
24 | Hathras | HRS | NCR-A | 37024 | 1296.38 |  | MILESTONE-2 | Section#1: CPYZ-Tundla | S |  | Completed | 2025-05-27 | Completed | 2025-08-06 | Yes | 160 KMPH DATS Tested and Sent to field | Completed and Signed By Rly. | 11-8-2025 10-02-2026 |  | 160KMPH Dats Tetsing Completed. AFTC Removed Dats Testing Completed |  | Completed & Signed by Raiways | 2025-08-11
25 | LSC-38 | HRS-LSC-38-PRA | NCR-A | 37025 | 1291.647 |  | MILESTONE-2 | Section#1: CPYZ-Tundla | L |  | Completed | 2025-05-27 | Completed | 2025-10-31 | Yes | 160 KMPH DATS Tested and Sent to field | Completed and Signed By Rly. | 2025-07-15 |  |  |  | Completed & Signed by Raiways | 2025-07-15
26 | Pora | PRA | NCR-A | 37026 | 1285.83 |  | MILESTONE-2 | Section#1: CPYZ-Tundla | S |  | Completed | 2025-05-27 | Completed | 2025-10-30 | Yes | 160 KMPH DATS Tested and Sent to field | Completed and Signed By Rly. | 14-07-2025 10-02-2026 |  | 160KMPH Dats Tetsing Completed. AFTC Removed Dats Testing Completed |  | Completed & Signed by Raiways | 2025-07-14
27 | LSC-40 | PRA-LSC-40-JLS | NCR-A | 37027 | 1282.6 |  | MILESTONE-2 | Section#1: CPYZ-Tundla | L |  | Completed | 2025-05-27 | Completed | 2025-07-07 | Yes | 160 KMPH DATS Tested and Sent to field | Completed and Signed By Rly. | 2025-07-11 |  |  |  | Completed & Signed by Raiways | 2025-07-11
28 | Jalesar Road | JLS | NCR-A | 37028 | 1276.41 |  | MILESTONE-2 | Section#1: CPYZ-Tundla | S |  | Completed | 2025-05-27 | Completed | 2025-10-07 | Yes | 160 KMPH DATS Tested and Sent to field | Completed and Signed By Rly. | 12-072025 09-02-2026 |  | 160KMPH Dats Tetsing Completed. AFTC Removed Dats Testing Completed |  | Completed & Signed by Raiways | 2025-07-12
29 | Chamrola | CMR | NCR-A | 37029 | 1269.95 |  | MILESTONE-2 | Section#1: CPYZ-Tundla | S |  | Completed | 2025-05-24 | Completed | 2025-07-17 | Yes | 160 KMPH DATS Tested and Sent to field | Completed and Signed By Rly. | 16-07-2025 09-02-2026 |  | 160KMPH Dats Tetsing Completed. AFTC Removed Dats Testing Completed |  | Completed & Signed by Raiways | 2025-07-16
30 | Barhan | BRN | NCR-A | 37030 | 1263.22 |  | MILESTONE-2 | Section#1: CPYZ-Tundla | S |  | Completed | 2025-05-27 | Completed | 2025-08-08 | Yes | 160 KMPH DATS Tested and Sent to field | Completed and Signed By Rly. | 25-07-2025 10-02-2026 |  | 160KMPH Dats Tetsing Completed. AFTC Removed Dats Testing Completed |  | Completed & Signed by Raiways | 2025-07-25
31 | Mitawali | MTI | NCR-A | 37031 | 1255.343 |  | MILESTONE-2 | Section#1: CPYZ-Tundla | S |  | Completed | 2025-05-27 | Completed | 2025-09-19 | Yes | 160 KMPH DATS Tested and Sent to field | Completed and Signed by Rly. | 17-7-2025 11-02-2026 |  | 160KMPH Dats Tetsing Completed. AFTC Removed Dats Testing Completed |  | Completed & Signed by Raiways | 2025-07-17
32 | Tundla | TDL | NCR-A | 37032 | 1248.881 |  | MILESTONE-4 | Section#1: CPYZ-Tundla | S |  | Work In Progress |  | Pending |  |  |  | Pending |  |  |  |  | Pending
33 | LSC-49 | TDL-LSC-49-HNG | NCR-A | 37033 | 1244.172 |  | MILESTONE-4 | Section#2: Tundla - CNB | L |  | Work In Progress |  | Pending |  |  |  | Pending |  |  |  |  | Pending
34 | Hirangaon | HNG | NCR-A | 37034 | 1239.75 |  | MILESTONE-3 | Section#2: Tundla - CNB | S |  | Completed | 2025-05-07 | Completed | 10/10/2025 10-02-2026 | Yes | 130 KMPH DATS Tested and Sent to field 160 KMPH DATS Tested and Sent to field | Completed and Signed by Rly. | 2026-01-14 |  | 160KMPH Dats Testing Completed |  | Pending
35 | Firozabad | FZD | NCR-A | 37035 | 1232.02 |  | MILESTONE-3 | Section#2: Tundla - CNB | S |  | Completed | 2025-05-07 | Completed | 14-10-2025 13-01-2026 | Yes | 130 KMPH DATS Tested and Sent to field 160 KMPH DATS Tested and Sent to field | Completed and Signed by Rly. | 2026-01-20 |  | 160KMPH Dats Testing Completed |  | Pending
36 | LSC-54 | FZD-LSC-54-MNR | NCR-A | 37036 | 1224.99 |  | MILESTONE-3 | Section#2: Tundla - CNB | L |  | Completed | 2025-05-07 | Completed | 22-10-2025 13-01-2026 | Yes | 130 KMPH DATS Tested and Sent to field 160 KMPH DATS Tested and Sent to field | Completed and Signed by Rly. | 2026-01-21 |  | 160KMPH Dats Testing Completed |  | Pending
37 | Makkhanpur | MNR | NCR-A | 37037 | 1221.77 |  | MILESTONE-3 | Section#2: Tundla - CNB | S |  | Completed | 2025-05-07 | Completed | 2026-01-22 |  | 160 KMPH DATS Tested and Sent to field | Work In Progress |  |  | 160KMPH Dats Testing In Progress |  | Pending
38 | LSC-56 | MNR-LSC-56-SKB | NCR-A | 37038 | 1215.7 |  | MILESTONE-3 | Section#2: Tundla - CNB | L |  | Completed | 2025-05-07 | Completed | 2026-02-07 |  | Pending Due to Approved Toc & Diff Reports. | Pending |  |  |  |  | Pending
39 | Shikohabad | SKB | NCR-A | 37039 | 1212.02 |  | MILESTONE-3 | Section#2: Tundla - CNB | S |  | Completed | 2025-05-07 | Completed | 2026-02-05 |  | Pending Due to Approved Toc. | Pending |  |  |  |  | Pending
40 | LSC-57 | SKB-LSC-57-KAA | NCR-A | 37040 | 1208.742 |  | MILESTONE-3 | Section#2: Tundla - CNB | L |  | Completed | 2025-05-07 | Completed | 2026-02-27 |  | 160 KMPH DATS Tested and Sent to field | Pending |  |  |  |  | Pending
41 | Kaurara | KAA | NCR-A | 37041 | 1201.13 |  | MILESTONE-3 | Section#2: Tundla - CNB | S |  | Completed | 2025-05-07 | Completed | 2026-02-19 |  | 160 KMPH DATS Tested and Sent to field | Pending |  |  |  |  | Pending
42 | LSC-61 | KAA-LSC-61-BDN | NCR-A | 37042 | 1195.33 |  | MILESTONE-3 | Section#2: Tundla - CNB | L |  | Completed | 2025-05-07 | Completed | 9/12/2025 26/02/2026 | Yes | 130 KMPH DATS Tested and Sent to field 160 KMPH DATS Tested and Sent to field | Completed and Signed by Rly. | 2025-08-10 |  | 130KMPH Dats Testing Completed |  | Completed & Signed by Raiways |  |  | 130KMPH Dats Testing Completed
44 | ECUU-60 | BDN-ECU-60_BBL | NCR-A | 37044 | 1192.07 |  | MILESTONE-3 | Section#2: Tundla - CNB | L |  | Completed | 2025-05-01 | Completed | 5/10/2025 02/02/2026 | Yes | 130 KMPH DATS Tested and Sent to field 160 KMPH DATS Tested and Sent to field | Completed and Signed by Rly. | 2025-10-22 |  | 130KMPH Dats Testing Completed |  | Completed & Signed by Raiways |  |  | 130KMPH Dats Testing Completed
43 | Bhadan | BDN | NCR-A | 37043 | 1186.825 |  | MILESTONE-3 | Section#2: Tundla - CNB | S |  | Completed | 2025-05-01 | Completed | 5/5/2025 26/02/2026 | Yes | 130 KMPH DATS Tested and Sent to field 160 KMPH DATS Tested and Sent to field | Completed and Signed by Rly. | 2025-10-22 |  | 130KMPH Dats Testing Completed |  | Completed & Signed by Raiways |  |  | 130KMPH Dats Testing Completed
45 | Balrai | BBL | NCR-A | 37045 | 1181.33 |  | MILESTONE-3 | Section#2: Tundla - CNB | S |  | Completed | 2025-05-01 | Completed | 5/10/2025 02/02/2026 | Yes | 130 KMPH DATS Tested and Sent to field 160 KMPH DATS Tested and Sent to field | Completed and Signed by Rly. | 2025-08-10 |  | 130KMPH Dats Testing Completed |  | Completed & Signed by Raiways |  |  | 130KMPH Dats Testing Completed
46 | LSC-65 | BBL-LSC-65-JGR | NCR-A | 37046 | 1175.589 |  | MILESTONE-3 | Section#2: Tundla - CNB | L |  | Completed | 2025-05-01 | Completed | 5/9/2025 03/02/2026 | Yes | 130 KMPH DATS Tested and Sent to field 160 KMPH DATS Tested and Sent to field | Completed and Signed by Rly. | 2025-10-10 |  | 130KMPH Dats Testing Completed |  | Completed & Signed by Raiways |  |  | 130KMPH Dats Testing Completed
47 | Jaswantnagar | JGR | NCR-A | 37047 | 1172.88 |  | MILESTONE-3 | Section#2: Tundla - CNB | S |  | Completed | 2025-05-01 | Completed | 5/13/2025 04/02/2026 | Yes | 130 KMPH DATS Tested and Sent to field 160 KMPH DATS Tested and Sent to field | Completed and Signed by Rly. | 2025-10-14 |  | 130KMPH Dats Testing Completed |  | Work In Progress |  |  | 130KMPH Dats Testing In Progress
48 | Sarai Bhopat | SB | NCR-A | 37048 | 1164.96 |  | MILESTONE-3 | Section#2: Tundla - CNB | S |  | Completed | 2025-05-01 | Completed | 5/16/2025 06/02/2026 | Yes | 130 KMPH DATS Tested and Sent to field 160 KMPH DATS Tested and Sent to field | Completed and Signed by Rly. | 2025-10-19 |  | 130KMPH Dats Testing Completed |  | Work In Progress |  |  | 130KMPH Dats Testing In Progress
49 | LSC-69 | SB-LSC-69-ETW | NCR-A | 37049 | 1159.572 |  | MILESTONE-3 | Section#2: Tundla - CNB | L |  | Completed | 2025-05-12 | Completed | 5/15/2025 18/02/2026 | Yes | 130 KMPH DATS Tested and Sent to field 160 KMPH DATS Tested and Sent to field | Pending |  |  |  |  | Pending
50 | Etawah Junction | ETW | NCR-A | 37050 | 1156.755 |  | MILESTONE-3 | Section#2: Tundla - CNB | S |  | Completed | 2025-08-13 | Completed | 2026-02-16 |  | 160 KMPH DATS Tested and Sent to field | Work In Progress |  |  | 160kmph Dats Testing In Progress |  | Pending
51 | LSC-74 | ETW-LSC-74-EKL | NCR-A | 37051 | 1150.399 |  | MILESTONE-3 | Section#2: Tundla - CNB | L |  | Completed | 2025-05-12 | Completed | 2026-02-27 |  | 160 KMPH DATS Tested and Sent to field | Pending |  |  |  |  | Pending
52 | Ekdil | EKL | NCR-A | 37052 | 1146.69 |  | MILESTONE-3 | Section#2: Tundla - CNB | S |  | Completed | 2025-05-04 | Work In Progress | 2025-07-14 | Yes | 130 KMPH DATS Tested and Sent to field 160 KMPH DATS Testing In Progress. | Completed and Signed by Rly. | 2025-12-10 |  | 130KMPH Dats Testing Completed |  | Completed & Signed by Raiways |  |  | 130KMPH Dats Testing Completed
53 | LSC-76 | EKL-LSC-76-BTN | NCR-A | 37053 | 1141.25 |  | MILESTONE-3 | Section#2: Tundla - CNB | L |  | Completed | 2025-05-04 | Work In Progress | 2025-09-05 | Yes | 130 KMPH DATS Tested and Sent to field 160 KMPH DATS Testing In Progress | Completed and Signed by Rly. | 2025-10-13 |  | 130KMPH Dats Testing Completed |  | Work In Progress
54 | Bharthana | BNT | NCR-A | 37054 | 1136.79 |  | MILESTONE-3 | Section#2: Tundla - CNB | S |  | Completed | 2025-06-04 | Work In Progress | 2025-09-09 | Yes | 130 KMPH DATS Tested and Sent to field 160 KMPH DATS TESTING IN PROGRESS | Completed and Signed by Rly. | 2025-10-18 |  | 130KMPH Dats Testing Completed |  | Completed & Signed by Raiways |  |  | 130KMPH Dats Testing Completed
55 | LSC-79 | BNT-LSC-79-SHW | NCR-A | 37055 | 1132.2 |  | MILESTONE-3 | Section#2: Tundla - CNB | L |  | Completed | 2025-06-04 | Completed | 14-07-2025 26-02-2026 | Yes | 130 KMPH DATS Tested and Sent to field 160 KMPH DATS Tested and Sent to field | Completed and Signed by Rly. | 2025-11-27 |  | 130KMPH Dats Testing Completed |  | Work In Progress
56 | Samhon | SHW | NCR-A | 37056 | 1126.32 |  | MILESTONE-3 | Section#2: Tundla - CNB | S |  | Completed | 2025-07-12 | Work In Progress |  | Yes | 130 KMPH DATS Tested and Sent to field 160 KMPH DATS TESTING IN PROGRESS | Completed and Signed by Rly. | 2025-01-12 |  | 130KMPH Dats Testing Completed |  | Pending
57 | LSC-81 | SHW-LSC-81-ULD | NCR-A | 37057 | 1122.86 |  | MILESTONE-3 | Section#2: Tundla - CNB | L |  | Completed | 2025-06-04 | Completed | 09-07-2025 31-01-2026 | Yes | 130 KMPH DATS Tested and Sent to field 160 KMPH DATS Tested and Sent to field | Completed and Signed by Rly. | 2025-10-25 |  | 130KMPH Dats Testing Completed. 160KMPH Dats Testing Completed |  | Completed & Signed by Raiways | 2026-02-03
58 | Achalda | ULD | NCR-A | 37058 | 1117.18 |  | MILESTONE-3 | Section#2: Tundla - CNB | S |  | Completed | 2025-06-04 | Completed | 09-07-2025 24-01-2026 | Yes | 130 KMPH DATS Tested and Sent to field 160 KMPH DATS Tested and Sent to field | Completed and Signed by Rly. | 29-11-2025 30-01-2026 |  | 130KMPH Dats Testing Completed. 160KMPH Dats Testing Completed |  | Completed & Signed by Raiways | 2026-09-02 |  | 160KMPH Dats Testing Completed
59 | Pata Railway | PTX | NCR-A | 37059 | 1108.89 |  | MILESTONE-3 | Section#2: Tundla - CNB | S |  | Completed | 2025-06-04 | Completed | 7-9-2025 02-12-2025 | Yes | 130 KMPH DATS Tested and Sent to field 160 KMPH DATS Tested and Sent to field | Completed and Signed by Rly. | 2025-06-12 |  | 160KMPH DATS Testing Completed & Released for SAT. |  | Completed & Signed by Raiways | 2026-02-03
60 | Phaphund | PHD | NCR-A | 37060 | 1100.42 |  | MILESTONE-4 | Section#2: Tundla - CNB | S |  | Completed | 2025-06-04 | Completed | 29-10-2025 10-12-2025 | Yes | 130 KMPH DATS Tested and Sent to field 160 KMPH DATS Tested and Sent to field | Completed and Signed by Rly. | 2025-11-12 |  | 160KMPH DATS Testing Completed & Released for SAT. |  | Completed & Signed by Raiways | 2026-02-20 |  | 160KMPH Dats Testing Completed
61 | LSC-87 | PHD-LSC-87-KNS | NCR-A | 37061 | 1096.705 |  | MILESTONE-4 | Section#2: Tundla - CNB | L |  | Completed | 2025-06-04 | Completed | 10-11-2025 04-12-2025 | Yes | 130 KMPH DATS Tested and Sent to field 160 KMPH DATS Tested and Sent to field | Completed and Signed by Rly. | 2025-10-12 |  | 160KMPH DATS Testing Completed & Released for SAT. |  | Work In Progress
62 | Kanchausi | KNS | NCR-A | 37062 | 1091.47 |  | MILESTONE-4 | Section#2: Tundla - CNB | S |  | Completed | 2025-06-04 | Completed | 11-11-2025 16-12-2025 | Yes | 130 KMPH DATS Tested and Sent to field 160 KMPH DATS Tested and Sent to field | Completed and Signed by Rly. | 2025-12-18 |  | 160KMPH DATS Testing Completed & Released for SAT. |  | Completed & Signed by Raiways | 2026-02-24 |  | 160KMPH Dats Testing Completed
63 | LSC-90 | KNS-LSC-90-JJK | NCR-A | 37063 | 1086.493 |  | MILESTONE-4 | Section#2: Tundla - CNB | L |  | Completed | 2025-06-04 | Completed | 17-11-2025 09-12-2025 | Yes | 130 KMPH DATS Tested and Sent to field 160 KMPH DATS Tested and Sent to field | Completed and Signed by Rly. | 2025-12-16 |  | 160KMPH DATS Testing Completed & Released for SAT. |  | Pending
64 | Jhinjhak | JJK | NCR-A | 37064 | 1080.42 |  | MILESTONE-4 | Section#2: Tundla - CNB | S |  | Completed | 2025-06-04 | Completed | 20-11-2025 12-12-2025 | Yes | 130 KMPH DATS Tested and Sent to field 160 KMPH DATS Tested and Sent to field | Completed and Signed by Rly. | 2025-12-15 |  | 160KMPH DATS Testing Completed & Released for SAT. |  | Completed & Signed by Raiways | 2026-02-25 |  | 160KMPH Dats Testing Completed
65 | LSC-93 | jjk-LSC-93-AAP | NCR-A | 37065 | 1074.45 |  | MILESTONE-4 | Section#2: Tundla - CNB | L |  | Completed | 2025-06-04 | Completed | 21-11-2025 13-12-2025 | Yes | 130 KMPH DATS Tested and Sent to field 160 KMPH DATS Tested and Sent to field | Completed and Signed by Rly. | 2025-12-16 |  | 160KMPH DATS Testing Completed & Released for SAT. |  | Pending
66 | Ambiapur | AAP | NCR-A | 37066 | 1070.4 |  | MILESTONE-4 | Section#2: Tundla - CNB | S |  | Completed | 2025-06-04 | Completed | 2025-12-17 |  | 160 KMPH DATS Tested and Sent to field | Completed and Signed by Rly. | 2025-12-20 |  | 160KMPH DATS Testing Completed & Released for SAT. |  | Pending
67 | LSC-96 | AAP-LSC-96-RRH | NCR-A | 37067 | 1064.39 |  | MILESTONE-4 | Section#2: Tundla - CNB | L |  | Completed | 2025-06-04 | Completed | 2025-12-18 |  | 160 KMPH DATS Tested and Sent to field | Completed and Signed by Rly. | 2025-12-16 |  | 160KMPH DATS Testing Completed & Released for SAT. |  | Pending
68 | Rura Railway | RRH | NCR-A | 37068 | 1061.59 |  | MILESTONE-4 | Section#2: Tundla - CNB | S |  | Completed | 2025-06-04 | Completed | 2025-12-24 |  | 160 KMPH DATS Tested and Sent to field | Completed and Signed by Rly. | 2025-12-27 |  | 160KMPH DATS Testing Completed & Released for SAT. |  | Pending
69 | ECUU-88 | RRH-ECUU-88-MTO | NCR-A | 37069 | 1056.56 |  | MILESTONE-4 | Section#2: Tundla - CNB | L |  | Completed | 2025-06-04 | Completed | 2025-12-26 |  | 160 KMPH DATS Tested and Sent to field | Completed and Signed by Rly. | 2025-12-29 |  | 160KMPH DATS Testing Completed & Released for SAT. |  | Pending
70 | Maitha | MTO | NCR-A | 37070 | 1049.9 |  | MILESTONE-4 | Section#2: Tundla - CNB | S |  | Completed | 2025-06-10 | Completed | 2025-12-29 |  | 160 KMPH DATS Tested and Sent to field | Completed and Signed by Rly. | 2026-05-01 |  | 160KMPH DATS Testing Completed & Released for SAT. |  | Pending
71 | LSC-101 | MTO-LSC-101-BPU | NCR-A | 37071 | 1045.13 |  | MILESTONE-4 | Section#2: Tundla - CNB | L |  | Completed | 2025-06-10 | Pending |  |  |  | Pending |  |  |  |  | Pending
72 | Bhaupur | BPU | NCR-A | 37072 | 1039.93 |  | MILESTONE-4 | Section#2: Tundla - CNB | S |  | Pending |  | Pending |  |  |  | Pending |  |  |  |  | Pending
73 | LSC-104 | BPU-LSC-104-PNKD | NCR-A | 37073 | 1034.77 |  | MILESTONE-4 | Section#2: Tundla - CNB | L |  | Pending |  | Pending |  |  |  | Pending |  |  |  |  | Pending
74 | Panki | PNKD | NCR-A | 37074 | 1028.55 |  | MILESTONE-4 | Section#2: Tundla - CNB | S |  | Pending |  | Pending |  |  |  | Pending |  |  |  |  | Pending
75 | Kanpur Goods Marshal | GMC | NCR-A | 37075 | 1021.15 |  | MILESTONE-4 | Section#2: Tundla - CNB | S |  | Pending |  | Pending |  |  |  | Pending |  |  |  |  | Pending
76 | Kanpur -Loco | CNBL | NCR-A | 37076 | 1017.34 |  | MILESTONE-4 | Section#2: Tundla - CNB | S |  | Pending |  | Pending |  |  |  | Pending |  |  |  |  | Pending
77 | Near Kanpur Central | CNB | NCR-A | 37101 | 1019.75 |  | MILESTONE-3 | Section#3: CNB - Subedarganj | S |  | Pending |  | Pending |  |  |  | Pending |  |  |  |  | Pending
78 | Chandari | CNBI | NCR-B | 37102 | 1015.25 |  | MILESTONE-3 | Section#3: CNB - Subedarganj | S |  | Completed | 2025-04-28 | Completed | 2025-09-13 | Yes | 100% Completed - As on 13-09-2025 | Completed and Signed by Rly. | 2025-08-12 |  |  |  | Pending
79 | Chakeri | CHK | NCR-B | 37103 | 1008.14 |  | MILESTONE-3 | Section#3: CNB - Subedarganj | S |  | Completed | 2025-04-27 | Completed | 2025-08-26 | Yes | 100% Completed - As on 26-08-2025 | Completed and Signed by Rly. | 2025-09-05 | Yes |  |  | Completed & Signed by Raiways | 2025-09-13
80 | Rooma | RXM | NCR-B | 37104 | 1003.89 |  | MILESTONE-3 | Section#3: CNB - Subedarganj | S |  | Completed | 2025-04-27 | Completed | 2025-08-22 | Yes | 100% Completed - As on 22-08-2025 | Completed and Signed by Rly. | 2025-09-16 | Yes |  |  | Completed & Signed by Raiways | 2025-09-25
81 | Sirsaul | SSL | NCR-B | 37105 | 997.14 |  | MILESTONE-3 | Section#3: CNB - Subedarganj | S |  | Completed | 2025-04-27 | Completed | 2025-06-20 | Yes | 100% Completed - As on 20-06-2025 | Completed and Signed by Rly. | 2025-09-01 | Yes |  |  | Completed & Signed by Raiways | 2025-09-06
82 | Prempur | PMPR | NCR-B | 37106 | 991.2 |  | MILESTONE-3 | Section#3: CNB - Subedarganj | S |  | Completed | 2025-04-27 | Completed | 2025-06-11 | Yes | 100% Completed - As on 11-06-2025 | Completed and Signed by Rly. | 2025-08-29 | Yes |  |  | Completed & Signed by Raiways | 2025-08-30
83 | Karbigwan | KBN | NCR-B | 37107 | 985.93 |  | MILESTONE-3 | Section#3: CNB - Subedarganj | S |  | Completed | 2025-04-27 | Completed | 2025-07-06 | Yes | 100% Completed - As on 06-07-2025 | Completed and Signed by Rly. | 27-08-2025 20-01-2026 | Yes |  |  | Completed & Signed by Raiways | 2025-08-28
84 | Aung | AUNG | NCR-B | 37108 | 979.32 |  | MILESTONE-3 | Section#3: CNB - Subedarganj | S |  | Completed | 2025-05-25 | Completed | 2025-06-05 | Yes | 100% Completed - As on 05-06-2025 | Completed and Signed by Rly. | 2025-08-21 | Yes |  |  | Completed & Signed by Raiways | 2025-08-22
85 | Bindki Road | BKO | NCR-B | 37109 | 973.55 |  | MILESTONE-3 | Section#3: CNB - Subedarganj | S |  | Completed | 2025-04-24 | Completed | 2025-05-27 | Yes | 100% Completed - As on 27-05-2025 | Completed and Signed by Rly. | 2025-08-23 | Yes |  |  | Completed & Signed by Raiways | 2025-09-04
86 | KanspurGugauli | KSQ | NCR-B | 37110 | 965.64 |  | MILESTONE-2 | Section#3: CNB - Subedarganj | S |  | Completed | 2025-04-24 | Completed | 2025-05-09 | Yes | 100% Completed - As on 09-05-2025 | Completed and Signed by Rly. | 22-08-2025 23-12-2025 | Yes |  |  | Completed & Signed by Raiways | 2025-08-23
87 | Malwan | MWH | NCR-B | 37111 | 958.31 |  | MILESTONE-2 | Section#3: CNB - Subedarganj | S |  | Completed | 2025-04-24 | Completed | 2025-05-21 | Yes | 100% Completed - As on 21-05-2025 | Completed and Signed by Rly. | 2025-08-21 | Yes |  |  | Completed & Signed by Raiways | 2025-08-21
88 | Malwan-Kurastikalan | MWH- RH2- KKS | NCR-B | 37112 | 953.31 |  | MILESTONE-2 | Section#3: CNB - Subedarganj | R |  | Completed | 2025-04-24 | Completed | 2025-05-19 | Yes | 100% Completed - As on 19-05-2025 | Completed and Signed by Rly. | 2024-04-06 | Yes |  |  | Completed & Signed by Raiways | 2025-08-21
89 | Kurasti Kalan | KKS | NCR-B | 37113 | 949.23 |  | MILESTONE-2 | Section#3: CNB - Subedarganj | S |  | Completed | 2025-04-24 | Completed | 2025-05-16 | Yes | 100% Completed - As on 16-05-2025 | Completed and Signed By Rly. | 2025-12-08 | Yes |  |  | Completed & Signed by Raiways | 2025-08-14
90 | Fatehpur | FTP | NCR-B | 37114 | 942.19 |  | MILESTONE-2 | Section#3: CNB - Subedarganj | S |  | Completed | 2025-05-25 | Completed | 2025-05-05 | Yes | 100% Completed - As on 05-05-2025 | Completed and Signed by Rly. | 2025-07-14 | Yes |  |  | Completed & Signed by Raiways | 2025-07-21
91 | Ramva | RAMA | NCR-B | 37115 | 936.31 |  | MILESTONE-2 | Section#3: CNB - Subedarganj | S |  | Completed | 2025-04-24 | Completed | 2025-05-06 | Yes | 100% Completed - As on 06-05-2025 | Completed and Signed by Rly. | 2025-07-07 | Yes |  |  | Completed & Signed by Raiways | 2025-07-22 |  | SAT was performed on 08-07-2025 and repeated on 22-07-2025 owing to necessary changes.
92 | Faizullapur | FYZ | NCR-B | 37116 | 930.94 |  | MILESTONE-2 | Section#3: CNB - Subedarganj | S |  | Completed | 2025-04-24 | Completed | 2025-05-05 | Yes | 100% Completed - As on 05-05-2025 | Completed and Signed by Rly. | 2025-07-03 | Yes |  |  | Completed & Signed by Raiways | 2025-07-19
93 | Rasulabad-Faizullapur | RUB- RH2-FYZ | NCR-B | 37117 | 927.66 |  | MILESTONE-2 | Section#3: CNB - Subedarganj | R |  | Completed | 2025-04-24 | Completed | 2025-05-05 | Yes | 100% Completed - As on 05-05-2025 | Completed and Signed by Rly. | 2025-06-14 | Yes |  |  | Completed & Signed by Raiways | 2025-07-29
94 | Rasulabad | RUB | NCR-B | 37118 | 922.04 |  | MILESTONE-2 | Section#3: CNB - Subedarganj | S |  | Completed | 2025-04-24 | Completed | 2025-05-05 | Yes | 100% Completed - As on 05-05-2025 | Completed and Signed by Rly. | 2025-06-06 | Yes |  |  | Completed & Signed by Raiways | 2025-06-17
95 | SathNaraini | SNIE | NCR-B | 37119 | 914.91 |  | MILESTONE-2 | Section#3: CNB - Subedarganj | S |  | Completed | 2025-04-24 | Completed | 2025-04-30 | Yes | 100% Completed - As on 30-04-2025 | Completed and Signed by Rly. | 2025-02-06 | Yes |  |  | Completed & Signed by Raiways | 2025-06-15
96 | Khaga | KGA | NCR-B | 37120 | 907.69 |  | MILESTONE-2 | Section#3: CNB - Subedarganj | S |  | Completed | 2025-04-19 | Completed | 2025-04-30 | Yes | 100% Completed - As on 30-04-2025 | Completed and Signed by Rly. | 2025-06-28 | Yes |  |  | Completed & Signed by Raiways | 2025-06-22
97 | Katoghan | KTCE | NCR-B | 37121 | 900.65 |  | MILESTONE-2 | Section#3: CNB - Subedarganj | S |  | Completed | 2025-04-19 | Completed | 2025-05-05 | Yes | 100% Completed - As on 05-05-2025 | Completed and Signed by Rly. | 29-05-2025 12-12-2025 | Yes |  |  | Completed & Signed by Raiways | 2025-06-20 |  | SAT was performed on 16-04-2025 and repeated on 20-06-2025 owing to necessary changes.
98 | Kanwar | KUW | NCR-B | 37122 | 894.1 |  | MILESTONE-2 | Section#3: CNB - Subedarganj | S |  | Completed | 2025-04-19 | Completed | 2025-04-30 | Yes | 100% Completed - As on 30-04-2025 | Completed and Signed by Rly. | 2025-05-23 | Yes |  |  | Completed & Signed by Raiways | 2025-06-11
99 | Athsarai | ASCE | NCR-B | 37123 | 889.1 |  | MILESTONE-2 | Section#3: CNB - Subedarganj | S |  | Completed | 2025-04-19 | Completed | 2025-04-30 | Yes | 100% Completed - As on 30-04-2025 | Completed and Signed by Rly. | 2025-05-17 | Yes |  |  | Completed & Signed by Raiways | 2025-05-21
100 | Sirathu | SRO | NCR-B | 37124 | 882.38 |  | MILESTONE-2 | Section#3: CNB - Subedarganj | S |  | Completed | 2025-04-19 | Completed | 2025-04-30 | Yes | 100% Completed - As on 30-04-2025 | Completed and Signed by Rly. | 2025-05-23 | Yes |  |  | Completed & Signed by Raiways | 2025-05-26
101 | Sirathu-Shujatpur | SRO-RH2-SJT | NCR-B | 37125 | 877.6 |  | MILESTONE-2 | Section#3: CNB - Subedarganj | R |  | Completed | 2025-04-19 | Completed | 2025-04-30 | Yes | 100% Completed - As on 30-04-2025 | Completed and Signed by Rly. | 2025-05-28 | Yes |  |  | Completed & Signed by Raiways | 2025-05-31
102 | Shujatpur | SJT | NCR-B | 37126 | 872.9 |  | MILESTONE-2 | Section#3: CNB - Subedarganj | S |  | Completed | 2025-04-19 | Completed | 2025-05-06 | Yes | 100% Completed - As on 06-05-2025 | Completed and Signed by Rly. | 2025-05-28 | Yes | Received Updated Report - 31-05-2025 |  | Completed & Signed by Raiways | 2025-05-31
103 | Bidanpur | BDNP | NCR-B | 37127 | 868.35 |  | MILESTONE-2 | Section#3: CNB - Subedarganj | S |  | Completed | 2025-04-19 | Completed | 2025-05-05 | Yes | 100% Completed - As on 05-05-2025 | Completed and Signed by Rly. | 2025-05-27 | Yes |  |  | Completed & Signed by Raiways | 2025-05-28
104 | Bharwari | BRE | NCR-B | 37128 | 862.73 |  | MILESTONE-1 | Section#3: CNB - Subedarganj | S |  | Completed | 2025-04-24 | Completed | 2025-04-30 | Yes | 100% Completed - As on 30-04-2025 | Completed and Signed by Rly. | 2025-05-23 | Yes |  |  | Completed & Signed by Raiways | 2025-05-24
105 | Manoharganj | MNJ | NCR-B | 37129 | 854.8 |  | MILESTONE-1 | Section#3: CNB - Subedarganj | S |  | Completed | 2025-04-24 | Completed | 2025-04-30 | Yes | 100% Completed - As on 30-04-2025 | Completed and Signed by Rly. | 2025-05-16 | Yes |  |  | Completed & Signed by Raiways | 2025-05-17
106 | Saiyid Sarawan | SYWN | NCR-B | 37130 | 847.26 |  | MILESTONE-1 | Section#3: CNB - Subedarganj | S |  | Completed | 2025-04-24 | Completed | 2025-04-30 | Yes | 100% Completed - As on 30-04-2025 | Completed and Signed by Rly. | 2025-05-14 | Yes |  |  | Completed & Signed by Raiways | 2025-05-16
107 | Manauri | MRE | NCR-B | 37131 | 842.98 |  | MILESTONE-1 | Section#3: CNB - Subedarganj | S |  | Completed | 2025-04-19 | Completed | 2025-04-30 | Yes | 100% Completed - As on 30-04-2025 | Completed and Signed by Rly. | 12-5-2025 01-07-2025 16-12-2025 | Yes |  |  | Completed & Signed by Raiways | 2025-07-12 |  | SAT was performed on 14-05-2025 and repeated on 04-07-2025 & 12-07-2025 owing to necessary changes.
108 | Bamhrauli-Manauri | BMU-RH2-MRE | NCR-B | 37132 | 838.244 |  | MILESTONE-1 | Section#3: CNB - Subedarganj | R |  | Completed | 2025-04-19 | Completed | 2025-04-30 | Yes | 100% Completed - As on 30-04-2025 | Completed and Signed by Rly. | 13-05-2025 02-07-2025 | Yes |  |  | Completed & Signed by Raiways | 2025-07-03 |  | SAT was performed on 15-05-2025 and repeated on 03-07-2025 owing to necessary changes.
109 | Bamhrauli | BMU | NCR-B | 37133 | 834.49 |  | MILESTONE-1 | Section#3: CNB - Subedarganj | S |  | Completed | 2025-04-19 | Completed | 2025-04-30 | Yes | 100% Completed - As on 30-04-2025 | Completed and Signed by Rly. | 09-05-2025 1-07-2025 | Yes |  |  | Completed & Signed by Raiways | 2025-07-03 |  | SAT was performed on 13-05-2025 and repeated on 02-07-2025 owing to necessary changes.
110 | Subedarganj (Prayagraj) | SFG | NCR-B | 37134 | 829.239 |  | MILESTONE-3 | Section#3: CNB - Subedarganj | S |  | Completed | 2025-04-19 | Completed | 2025-11-21 |  | 100% Completed - As on 21-11-2025 | Completed and Signed by Rly. | 2025-11-22 | Yes |  |  | Work In Progress | 2025-09-12 |  | Routes Pending Towards PRYJ
111 | New Location SFG-PRYJ | SFG-PRYJ | NCR-B | 37135 | 826.379 |  | MILESTONE-3 | Section#4: Subedarganj - DDU | L |  | Pending |  | Pending |  |  |  | Pending |  |  |  |  | Pending
112 | Prayagraj Junction | PRYJ | NCR-B | 37136 | 825.27 |  | MILESTONE-3 | Section#4: Subedarganj - DDU | S |  | Pending |  | Pending |  |  |  | Pending |  |  |  |  | Pending
113 | Naini | NYN | NCR-B | 37137 | 819 |  | MILESTONE-3 | Section#4: Subedarganj - DDU | S |  | Pending |  | Pending |  |  |  | Pending |  |  |  |  | Pending
114 | Prayagraj Chheoki | PCOI | NCR-B | 37138 | 816.65 |  | MILESTONE-3 | Section#4: Subedarganj - DDU | S |  | Pending |  | Pending |  |  |  | Pending |  |  |  |  | Pending
115 | Karchana-Chheoki | KCN- RH-2-COI | NCR-B | 37139 | 811.375 |  | MILESTONE-3 | Section#4: Subedarganj - DDU | R |  | ON Hold |  | Pending |  |  |  | Pending |  |  |  |  | Pending
116 | Karchana 3rd linePH-I Karchana 3rd linePH-II | KCN | NCR-B | 37140 | 807.43 |  | MILESTONE-3 | Section#4: Subedarganj - DDU | S |  | Work In Progress |  | Pending |  |  |  | Pending |  |  |  |  | Pending
117 | Bheerpur-Karchana | BEP-RH2-KCN | NCR-B | 37141 | 801.299 |  | MILESTONE-3 | Section#4: Subedarganj - DDU | R |  | ON Hold |  | Pending |  |  |  | Pending |  |  |  |  | Pending
118 | BHEERPUR-3rd LINE | BEP | NCR-B | 37142 | 798.32 |  | MILESTONE-3 | Section#4: Subedarganj - DDU | S |  | Work In Progress |  | Pending |  |  |  | Pending |  |  |  |  | Pending
119 | Bheerpur-Meja | BEP- RH-2-MJA | NCR-B | 37143 | 793.662 |  | MILESTONE-3 | Section#4: Subedarganj - DDU | R |  | ON Hold |  | Pending |  |  |  | Pending |  |  |  |  | Pending
120 | Meja Road | MJA | NCR-B | 37144 | 787.27 |  | MILESTONE-3 | Section#4: Subedarganj - DDU | S |  | Work In Progress |  | Pending |  |  |  | Pending |  |  |  |  | Pending
121 | Unchdih-Meja | UND-RH2-MJA | NCR-B | 37145 | 785/2-4 |  | MILESTONE-3 | Section#4: Subedarganj - DDU | R |  | ON Hold |  | Pending |  |  |  | Pending |  |  |  |  | Pending
122 | Unchdih Railway | UND | NCR-B | 37146 | 778.825 |  | MILESTONE-3 | Section#4: Subedarganj - DDU | S |  | Pending |  | Pending |  |  |  | Pending |  |  |  |  | Pending
123 | Mandah Road | MNF | NCR-B | 37147 | 770.77 |  | MILESTONE-4 | Section#4: Subedarganj - DDU | S |  | Pending |  | Pending |  |  |  | Pending |  |  |  |  | Pending
124 | Jigna | JIA | NCR-B | 37148 | 762.46 |  | MILESTONE-4 | Section#4: Subedarganj - DDU | S |  | Pending |  | Pending |  |  |  | Pending |  |  |  |  | Pending
125 | Gaipura Railway | GAE | NCR-B | 37149 | 755.41 |  | MILESTONE-4 | Section#4: Subedarganj - DDU | S |  | Pending |  | Pending |  |  |  | Pending |  |  |  |  | Pending
126 | Birohi-Gaipura | BEO-RH-1-GAE | NCR-B | 37150 | 750/16-18 |  | MILESTONE-4 | Section#4: Subedarganj - DDU | R |  | Pending |  | Pending |  |  |  | Pending |  |  |  |  | Pending
127 | Birohi | BEO | NCR-B | 37151 | 747.13 |  | MILESTONE-4 | Section#4: Subedarganj - DDU | S |  | Pending |  | Pending |  |  |  | Pending |  |  |  |  | Pending
128 | VINDYACHAL | BDL | NCR-B | 37152 | 743.21 |  | MILESTONE-4 | Section#4: Subedarganj - DDU | S |  | Pending |  | Pending |  |  |  | Pending |  |  |  |  | Pending
129 | Mirzapur | MZP | NCR-B | 37153 | 735.85 |  | MILESTONE-4 | Section#4: Subedarganj - DDU | S |  | Completed | 2025-05-05 | Completed | 2025-07-07 |  | Released for CFAT | Completed and Signed By Rly. | 2025-07-30 | Yes |  | Updated | Completed & Signed by Raiways | 2025-10-14
130 | Jhingura | JHG | NCR-B | 37154 | 727.53 |  | MILESTONE-4 | Section#4: Subedarganj - DDU | S |  | Completed | 2025-05-05 | Completed | 2025-07-12 |  | Released for CFAT | Completed and Signed By Rly. | 2025-09-27 | Yes |  | Updated | Completed & Signed by Raiways | 2025-10-17
131 | Pahara | PRE | NCR-B | 37155 | 720.12 |  | MILESTONE-4 | Section#4: Subedarganj - DDU | S |  | Completed | 2025-05-05 | Completed | 2025-07-16 |  | Released for CFAT | Completed and Signed by Rly. | 2025-09-29 |  |  | Updated | Completed & Signed by Raiways | 2025-10-25
132 | Dagmagpur | DAP | NCR-B | 37156 | 711.199 |  | MILESTONE-4 | Section#4: Subedarganj - DDU | S |  | Completed | 2025-05-05 | Completed | 2025-07-18 |  | Released for CFAT | Completed and Signed by Rly. | 2025-07-10 |  |  | Updated | Completed & Signed by Raiways | 2025-10-18
133 | Chunar Junction | CAR | NCR-B | 37157 | 704.77 |  | MILESTONE-4 | Section#4: Subedarganj - DDU | S |  | Completed | 2025-09-17 | Completed | 2026-01-14 |  | Released for CFAT | Work In Progress |  |  |  |  | Pending
134 | Kailahat-Chunar | KYT-RH-2-CAR | NCR-B | 37158 | 701.1 |  | MILESTONE-4 | Section#4: Subedarganj - DDU | R |  | Completed | 2025-09-17 | Completed | 2026-01-24 |  | Released for CFAT | Pending |  |  |  |  | Pending
135 | Kailahat | KYT | NCR-B | 37159 | 694.87 |  | MILESTONE-4 | Section#4: Subedarganj - DDU | S |  | Completed | 2025-09-17 | Completed | 2025-09-24 |  | Released for CFAT | Completed and Signed by Rly. | 2025-11-21 |  |  |  | Completed & Signed by Raiways | 2026-09-02
136 | RH1 | ARW -RH1 -KYT | NCR-B | 37160 | 690.35 |  | MILESTONE-4 | Section#4: Subedarganj - DDU | R |  | Completed | 2025-09-17 | Completed | 2025-09-26 |  | Released for CFAT | Completed and Signed by Rly. | 2025-12-24 |  |  |  | Work In Progress
137 | AHRAURA ROAD /NARAYANPUR BAZAR | ARW /NPBR | NCR-B | 37161 | 686.35 |  | MILESTONE-4 | Section#4: Subedarganj - DDU | S |  | Completed | 2025-09-17 | Completed | 2025-09-30 |  | Released for CFAT | Completed and Signed by Rly. | 2025-11-21 |  |  |  | Work In Progress
138 | JEONATHPUR | JEP | NCR-B | 37162 | 680.48 |  | MILESTONE-4 | Section#4: Subedarganj - DDU | S |  | Completed | 2025-09-17 | Completed | 2025-12-19 |  | Released for CFAT | Completed and Signed by Rly. | 2026-09-02 |  |  |  | Pending
139 | BH-K | BH-K | NCR-B | 37163 | 677.33 |  | MILESTONE-4 | Section#4: Subedarganj - DDU | R |  | Completed | 2025-09-17 | Completed | 2025-12-24 |  | Released for CFAT | Completed and Signed by Rly. | 2026-01-29 |  |  |  | Pending